## Slide 1: Applying Earned Value Management to Agile Software Development Programs
Bob Hunt
Michael Thompson
Gordon Kranz
Galorath Federal Incorporated

## Slide 2
Background to Agile
Agile/Hybrid Agile software development implementation
Establishing a process for developing the technical, cost and schedule baseline
Applying Earned Value Management to Agile Programs
Summary
Back Up
Agenda

## Slide 3: How Formal Is Agile?
Manifesto for Agile Software Development
“We are uncovering better ways of developing software by doing it and helping others do it.
Through this work we have come to value:
Individuals and interactions over processes and tools Working software over comprehensive documentation Customer collaboration over contract negotiation Responding to change over following a plan
That is, while there is value in the items on the right, we value the items on the left more.”
Agile is NOT a Method – it’s a mindset!
Individual Methods are Formal – sort-of

## Slide 4: Agile 101 – How It Works
Agile is a set of software development methods in which solutions evolve through collaboration
  Integrated teams include PeopleSoft SMEs to configure the product, PeopleSoft Developers, Data Integration Developers, and Testers
Development is iterative
  The traditional software development phases are seen as continuous activities
  Work is broken into smaller tasks
  Multiple iterations may be required to release a product
  Documentation is created as-built
For each iteration, a working product is demonstrated to stakeholders
Emphasizes value-driven approach
  The usual project constraints still apply
  Focusing on value allows most important
  functionality to be delivered first
Technology agnostic

## Slide 5: Agile 101 – Development Approach Metaphor
With Agile, we start with a concept: for several large software development programs, the COTS product is the starting point
Then, we iteratively build a rough version and validate it, slowly improving the definition and quality
The waterfall approach is akin to painting by numbers, as it calls for a fully formed idea at the start, which is built incrementally, piece by piece without flexibility

## Slide 6: Agile 101 – Key Agile Terminology
Term | Definition
Scrum | A framework for team collaboration on complex software projects. 1-10 people (have seen up to 20)
Sprint | A short multiple-week period where a team completely builds working, tested software. All phases of the SDLC are executed iteratively during a sprint – Analysis, Design, Code, Test. 1-6 weeks (have seen up to 13 weeks) (13 conveniently give 4 sprints per year)
Feature | A set of specifications that can be shown in a user demonstration and oriented on system capabilities.
Epic | A description of how work gets done using the new software (To-Be business process).
Spike | A special type of story used for research and prototyping activities, which can be functional or technical.
Backlog | A single definitive repository for all upcoming work. It consists primarily of future features intended to address user needs and deliver business benefits, as well as architectural features required to build the product.

## Slide 7: Agile Implementation
Feature/BP Demonstrations
7
To create working software product often and to demonstrate to the customer
Sprint Backlog
Sprint Burndown
Impediment List
Update Product Backlog
Sprint Planning Meeting
Daily Scrum/
Daily Work
Sprint Review
Demonstration
Product
Increment
Sprint
Retrospective
Scrum Process
Backlog
Ensures holistic activities and iterative processes
INTEGRITY INNOVATION EXCELLENCE

## Slide 8: Agile 101 – Sprint Breakdown
Sprint Planning Meeting
  Product owner and scrum team meet at the start of the sprint to review the sprint goal, and select the requirements/features and corresponding tasks to be accomplished.
Daily Scum/Daily Work
  Scrum team meets daily to review yesterday’s accomplishments, plan for today, and any blockers.
Sprint Review Demonstration
  Scrum team demonstrates sprint accomplishments (requirements and/or features implemented during that sprint) to the product owner.
Sprint Retrospective
  The scrum team meets to discuss what to keep doing, stop doing, and start doing. Focus on what is actionable for the next sprint.
Update Product Backlog
  The product owner continuously updates (adds to, reprioritizes, etc.) the product backlog.
PDR/CDR/TRR
Update Product Backlog
Sprint Planning Meeting
Daily Scrum/
Daily Work
Sprint Review
Demonstration
Product
Increment
Sprint
Retrospective
Scrum Process
Sprint Backlog
Sprint Burndown
Impediment List

## Slide 9: Agile 101 – Recap
Agile is a disciplined methodology.
Agile is not…
  …unlimited or uncontrolled scope.
  …unplanned.
  …undocumented.
  …unverified.
  …mini waterfall.
  …trial and error.
  …a synonym for flexible.
  …a synonym for fast.

## Slide 10: Agile 101 - Summary
Waterfall faces challenges in a large-scale ERP implementation.
  Significant effort to build and maintain momentum
  High risk of a resulting product that does not meet needs
Looking for an alternative:
  Best candidate is Scaled Agile Framework (SAFe)
  Lower risk implementation
  Produces better results, meets large software program’s vision
  Allows us to confirm that we are building the right thing
  Gets early buy-in
  Reduces the risk of rework when it is too late and more costly to change
  Improved understanding of progress and cost
Better software development process, better user experience:
  Break work into smaller, more manageable segments
  Measure progress based on working software product
  Drive functionality working on through to completion
  Emphasize showing working versions of product early and often to validate
  Use product to review whether it meets requirements – shift to As-Built documentation
  Use government time and resources better by reviewing software, not paper
  Use cumulative assembly testing for earlier validation of product
  Have automated regression test bed available on go-live

## Slide 11: Agile Building Blocks*
Sprints
Epic 1
Feature 1
User Story 1
Epic 2
Feature 2
User Story 2
Epic 2 Feature 3
User Story 3
Theme/Increment 1
Release 1 (made up of multiple Themes/Increments
Cost Estimating done at the Sprint Level
EVM work Packages identified at Epic or Theme level
* These “building blocks” are program specific and may be called by different names
Feature Point values applied to each Feature

## Slide 12: Hybrid Agile Development/Acquisition
Agile
Testing and Sustainment ?

## Slide 13: Earned Value Management Process

## Slide 14: Where Does EVM fit in?
As long as there is a plan and product, which can be measured EVM can be used
The product backlog defines the product, and sprints are used to time phase the work.
Status of each Sprint is rolled up at the EPIC Level, which in this example is the Control Account (CA)
  Below the EPIC is the Feature at the Work Package (WP) level, which breaks the EPIC into functional packages
  Features are decomposed into Stories and Story points
  Sprints are statused by, in this case, Stories and Story Points, which are maintained in an Agile Program Management Tool
As Features are completed the percent complete is rolled up to the EPIC level

## Slide 15: Documentation Traceability
Contractor CWBS Matrix
CSDR CWBS Matrix

## Slide 16: EVM – Agile Traceability
Initial Features Priorities & LOE. Xls
Epics
Features
# of SSS Requirements
Which Features are mapped to which Sub-
EPIC (WP)

## Slide 17: Progress Roll Up
AGILE Tool Provides Sprint Status
Story Points Assigned Feature Level
Sub-EPIC and Feature Completion
Rolled up to EPIC Level
Earned Value Taken at the EPIC Level
Progress at EPIC Level Rolled into EVM Progress
EPICS lowest level in the schedule
EVM Progress tracked in schedule at EPIC Level
EPIC Progress Rolled up Module Status

## Slide 18: Approach Allows Following Progress Reports
Earned Value Status at EPIC Level
Progress against
  % EPIC Completion
  % Module Completion
  % Feature Completion Total
  % SSS Completion
Metrics and Trends
  Feature Burn Down / Up
  EPIC Burn Down / Up
  SSS Burn Down / Up
  Sprint Velocity by Team and over time
Supports EAC Development from a variety of angles for cross verification

## Slide 19: Notional Sprint Data

## Slide 20: Notional Story Point Burndown Chart

## Slide 21: Notional Sprint Burndown Bar Chart

## Slide 22: Summary
Fixed Price and/or LOE contracts in the early phases should be written so that key “value-added” metrics are collected and reported during each increment
Estimators may have to employ a variety of software estimating methodologies within a single estimate to model the blended development approaches being utilized in today’s development environments
    An agile estimating process can be applied to each iteration/sprint
    Future Increments can be estimated based on most recent/successful IID performance
Cost estimators will have to scrutinize these programs like a schedule analyst might to determine the most likely IOC capabilities and associated date
    The number of increments are an important cost driver as well as an influential factor in uncertainty/risk modeling

## Slide 23: Summary
All of the estimation methods are susceptible to error, and require accurate historical data to be useful within the context of the organization
When developers and estimators use the same “proxy” for effort, there is more confidence in the estimate

## Slide 24: Recommended Reading
“The Death of Agile” blog
“Agile Hippies and The Death of the Iteration” blog
Story Point Inflation
5

## Slide 25: Endnotes
1, 2, 4, 10, 11: Larman, C. (2010). Agile and Iterative Development: A Manager's Guide.
3: Kilgore, J. (2012). Senior Associate, Kalman & Company, Inc.
5, 6, 7, 8: Agile Alliance. (2012). Agile Alliance. Retrieved 2012, from http://www.agilealliance.org
9: Coaching, T. L. (n.d.). Rally Software Scaling Software Agility.
12: Bittner, K., & Spence, I. (2006). Managing Iterative Software Development Projects. Addison-Wesley Professional.

## Slide 26: Additional References
Cohn, M. (2009). Succeeding with Agile Software Development using Scrum.
Dooley, J. (2011). Software Development and Professional Practice.
Gack, G. (2010). Managing the Black Hole.
George, J., & Rodger, J. (2010). Smart Data (Enterprise Performance Optimization Strategy).
Royce, W., Bittner, K., & Perrow, M. (2009). The Economics of Iterative Software Development: Steering Towards Better Business Results. Addision Wesley Professional.
Smith, G., & Sidky, A. (2009). Becoming Agile in an Imperfect World.
5

## Slide 27: Contact Information
Bob Hunt
    Email: BHunt@Galorath.com
    Phone: 703.201.0651
  Mike Thompson
    Email: mthompson@galorath.com
    Phone: 301.904.1103
  Gordon Kranz
    Email: gmkranz@eipm-llc.com
    Phone: 571.268.8168

## Slide 28: Back Up

## Slide 29: IT Project Success
Figure 1. Distribution of Success and Failure Across Project Sizes
Source: Gartner (June 2012)
20% to 30% Failures
Why they fail

## Slide 30: Five Estimating Methodologies
Methodology 1: Since many Agile programs are fixed price, it is often just a matter of labor rates times quantity
Methodology 2: Simple Build-up approach based on averages can be defined as:
    Sprint Team Size (SS) x Sprint length (Sp time) x Number of Sprints (# Sprints)
    Methodology 3: Structured approach based on established “velocity” – most often used internally by the developer since detailed/sensitive data are available to them
    Methodology 4: Automated Models approach based on a size metric – which may be difficult to quantify
    Methodology 5: Factor/Complexity approach based on data generated in early iterations

## Slide 31: What to measure

## Slide 32: Software Development
While there are many approaches to Software Development, they can generally be placed into 2 categories:
    Plan Driven – following a version of the Waterfall Development Process
    Iterative Driven – following a “version” of the Agile Development Process
  Plan Drive programs have an assumption of some reliable/realistic size metric, for example:
    Source Lines of Code (SLOC)
    Function Points
    Use Cases, User Stories, Web Pages

## Slide 33: What is Agile Software Development?
In the late 1990s, several methodologies received increasing public attention
Each had a different combination of old, new, and transmuted old ideas, but they all emphasized:
    Close collaboration between the programmer and business experts
    Face-to-face communication (as more efficient than written documentation)
    Frequent delivery of new deployable business value
    Tight, self-organizing teams
    And ways to craft the code and the team such that the inevitable requirements churn was not a crisis
5

## Slide 34: Agile – System View
NON-AGILE
R3 PBR
R3 CDR
R3 PDR
R5 PBR
R5 CDR
R5 PDR
R2 PBR
R2 CDR
R2 PDR
Application Development
Data
Infrastructure
AGILE TERRITORY
Full Application Fit/Gap
Personnel
Pay
SI Tools Fit/Gap
R2 RRE Prep
R3 RRE Prep
R4 PBR
R4 PDR
R4 CDR
DEVELOP ON CADENCE, RELEASE ON DEMAND
R3 PBR
R3 CDR
R3 PDR
R2 PBR
R2 CDR
R2 PDR
Prelim Data Maps
Final Data Maps
Build
Prelim Data Maps
Final Data Maps
Build
R5 PBR
R5 CDR
R5 PDR
Prelim Data Maps
Final Data Maps
Build
R4 PBR
R4 CDR
R4 PDR
Prelim Data Maps
Final Data Maps
Build
Cybersecurity
Environments Systems Management
Configuration Management
Systems Engineering
Auditing
Lifecycle Management
Integrated Logistics Support
Government Testing
Cumulative/Regression Personnel PLT
Release 3.0
WATERLINE
Release 1.0
Release 2.0
Legacy System Sunset Order
Cumulative/Regression Pay PLT
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Epic
Spike
Spike
Spike
Spike
Spike
Spike
Spike
Spike
Delta Fit/Gap
Delta Fit/Gap

## Slide 35: Agile Release and Sprint Backlog
Product Backlog
User Feedback,
Defects, and New Features
Analyze
Design
Test
Increasing use of Agile Methods
TRR
Agile methods can start earlier in the process because we are starting with a COTS product baseline.
Analyze
Design
Test
Configure
Release Backlog
Conduct Fit/Gap Build
Feature Backlog
Feature 2
Feature 1
Feature 3, Sprint 1
Feature 2, Sprint 1
Feature 2, Sprint 2
Feature 4, Sprint 1
Sprint Backlogs
Preliminary Design Planning
IBR
F/G
Analyze
Design
Test
Configure
Analyze
Design
Test
Build
Conduct Framework Build
Conduct High/Medium Priority Build
Conduct Low Priority Build
Feature 3, Sprint 2
Feature n…
Feature 1, Sprint 1
Feature 4, Sprint 2

## Slide 36: How to Scale
Agile methods are generally used for projects of smaller scope.
Scaled Agile Framework (SAFe) builds from Agile methods to provide a construct for large-scale implementations.
A playbook tailored to particular software program will inform the development of the IMS and form the basis to guide teams.
  Introduces features to bridge the gap between epics (business processes) and sprints.
  Introduces spikes to explore various approaches to address key foundational decisions.
INTEGRITY INNOVATION EXCELLENCE 36

## Slide 37: How to Define Work
.
Features will be classified as one of the following types:
  Framework: Foundational capabilities that need to be completed early as they will be leveraged throughout the solution.
  Core: Capabilities support transactional processing. These include setup tables that maintain valid values and capabilities to manage employee records.
  Self-Service: Any feature that has a self-service component is identified.
  Information: Reports, queries, dashboards.
  Data: Conversions and interfaces.
1 - Requirements are defined based on the Business Process.
2 - Requirements are grouped into features aligned with the delivered software product.
3 - Features are decomposed into tasks to be executed in sprints.

## Slide 38: How to Apply Agile in a Non-Agile World
38

## Slide 39
When performance is measured performance improves
Estimation processes are independent of tools
Galorath: Driving The State of the Art (10 Step Estimation Process)
Establish Estimate Scope
Establish Technical Baseline, Ground Rules, Assumptions
Collect Data
Estimate and Validate Software Size
Prepare Baseline Estimates
Quantify Risks and Risk Analysis
Review, Verify and Validate Estimate
Generate a Project Plan
Document Estimate and Lessons Learned
Track Project Throughout Development
We will use these 10 steps in our Estimation Process Improvement Program (EPIP)

## Slide 40: Fundamental Model Assumptions
Fundamental assumptions of most Software Estimating Models
There is a fixed relationship between size and effort, e.g.
  (Effort**n)*Time = Size/Technology
Results are then modified by current trends and analyses
Total effort can be distributed by a mathematical model; e.g. Weibull, Rayleigh

## Slide 41: Methodology 5: Factor/Complexity Approach
Scale | Functional Description | Effort Multipliers
- - - | Significantly less functionality to be delivered | 0.5
- - | Moderately less functionality to be delivered | 0.7
- | Slightly less functionality to be delivered | 0.9
= | Functionality equivalent to Increment X | 1.0
+ | Slightly more functionality to be delivered | 1.3
+ + | Moderately more functionality to be delivered | 1.7
+ + + | Significantly more functionality to be delivered | 2.0
Scale | Complexity Description | Effort Multipliers
- - | Significantly less complex | 0.7
- | Slightly less complex | 0.9
= | Complexity equivalent to Increment X | 1.0
+ | Slightly more complex | 1.3
+ + | Significantly more complex | 1.7
  These initial set of factors came from the environmental factor from traditional software cost models
    Because each Increment is a mini project, use a Rayleigh or simple Beta Curve (such as a 60/50 Beta curve) to phase costs