## Slide 1: Bottom Up Methods of Estimating Software SEPM and Non-DCTI Cost 2017 ICEAA Professional Development & Training Workshop
James R. Black
June 2017

## Slide 2: Bio
Presenter: James “Jay” Black has 13 years of cost estimating experience and currently works as a software project manager for the Administration for Children and Families within the U.S. Department of Health and Human Services. In this role, he supports the Grants Center of Excellence software suite used to administer 1200 grant programs in eight Federal departments. Jay has a Masters in Systems Engineering from Johns Hopkins University and holds a current CCE/A certification.
Jay worked for the Navy cost community (NAVAIR 4.2, NCCA, & NAVSEA 05C) from 2003 through 2015
For questions, comments, and/or feedback please email me at:
  James.robert.black@gmail.com
  James.black@acf.hhs.gov
If any material in this brief is of use to you now or later,
please email me, I’d love to know

## Slide 3: References & Abstract
References/Acknowledgements:
  Mike Popp’s observations on IEEE Standard 11207
  Tim Lawless observations on Systems Engineering/Program Management
  Cost Estimating Body of Knowledge (CEBoK) Module 1 Cost Estimating Basics
Presentation abstract:
  Systems Engineering/Program Management (SE/PM) and additional non-Design, Code, Test, and Integration (Non-DCTI) activities performed during software development efforts are often significant and drive estimates of total project costs
  Yet, cost estimates often omit the detailed research and analysis needed to adequately model SE/PM & Non-DCTI costs
  This brief will present bottom up methods useful for understanding and estimating these costs and share analysis of recent SE/PM & Non-DCTI data
This presentation is the result of practicing detailed actual cost data collection for a variety of platform and system estimates/analyses

## Slide 4: WBS is the Foundation
A Work Breakdown Structure (WBS) establishes a common frame of reference for relating job tasks to each other and relating project costs at the summary level of detail
  It provides a consistent and visible framework for specifying the objectives, labor, materials, and contracts of the system/program.
  The structure is used to define the total program/system by providing detailed definitions of individual elements required (via a WBS Dictionary)
A WBS should be tailored for each system or program for the purpose of capturing all the idiosyncrasies endemic to each system/program
Estimate uses a WBS that is at a level of detail appropriate to ensure that cost elements are neither omitted nor double-counted
Estimate is presented in a WBS fully traceable to the system specification
WBS structure is aligned to organizational structure performing the work; WBS element tasks are traceable to data, which is traceable back to the respective source documents
The WBS is the foundation and a common WBS speeds the uptake of information for the cost estimate’s audience
Per Cost Estimating Body of Knowledge (CEBoK) Module 1 Cost Est. Basics:

## Slide 5: WBS Example - MIL-STD-881C
For Department of Defense projects, WBS templates are provided in: MIL-STD-881C Work Breakdown Structures for Defense Material Items
An example WBS from MIL-STD-881C for an Automated Information System follows:
1.0 | Automated Information System (AIS) | 
1.1 | AIS Prime Mission Product (PMP) Release/Increment X | 
 | 1.1.1 | Custom Application Software 1…n
 | 1.1.2 | Enterprise Service Element 1…n
 | 1.1.3 | Enterprise Information System 1…n
 | 1.1.4 | External System Interface Development 1…n
 | 1.1.5 | AIS Platform Hardware
 | 1.1.6 | System Level Integration
1.2 | System Engineering | 
1.3 | Program Management | 
1.4 | Change Management | 
1.5 | System Test and Evaluation | 
1.6 | Training | 
1.7 | Data | 
1.8 | Peculiar Support Equipment | 
1.9 | Common Support Equipment | 
1.10 | Operational/Site Activation | 
1.11 | Industrial Facilities | 
1.12 | Initial Spares and Repair Parts | 
Design, Code, Test, & Integration (DCTI)
Element-level software development
Non-recurring, variable costs: driven by a software sizing measure, e.g. Source Lines of Code (SLOC)
So, what does it mean when estimators refer to “Non-DCTI” ?
“SE/PM” or “SEPM”
System-level activities related to software, hardware, and integration
Recurring, fixed costs: driven by a Level-of-Effort headcount mostly independent of software size
*
* Note: 1.2 & 1.3 also include system level integration efforts

## Slide 6: Software Cost Estimating Key Words
Design, Code, Test, & Integration (DCTI)
Systems Engineering & Program Management (SEPM)
“Non-DCTI” - In the presenter’s experience, Non-DCTI is the SEPM related to software development
  Exists as a recurring development activity
  Often begins before the start of non-recurring development activities (i.e. DCTI)
  Continues throughout the execution of DCTI activities
  Keep in mind: since Non-DCTI is not immediately identifiable in MIL-STD-881C, it can mean different things to different people
When estimating software costs: be diligent in identifying how effort is allocated to DCTI, Non-DCTI and/or SEPM

## Slide 7: IEEE Standard 12207
Fixed
Costs
IEEE = Institute of Electrical and Electronics Engineers
SEPM
System-level activities related to software, hardware, and integration
DCTI
Element-level software development
“Systems and Software Engineering - Software Life Cycle Processes”
IEEE 12207 is useful when differentiating between SEPM & DCTI

## Slide 8: Non-DCTI Estimating
When estimating Non-DCTI:
  For continued development on an existing system (e.g. future spiral or increment): collect SEPM FTE actuals from prior spirals/increments (e.g. from CCDRs 1921 & 1921-1)
  For a new system: collect SEPM FTE actuals for analogous systems (e.g. from CCDRs 1921 & 1921-1)
  Normalize collected data:
    Identify how representative prior FTEs are of future effort required
    Parse total FTEs to identify software efforts
Estimate Non-DCTI costs:
  First, use a bottom up estimating methodology: FTEs/year * Years of development * Labor Rate
  Then, use a crosscheck: DCTI cost or hours * Non-DCTI factor
Primary estimating approach: bottom up methodology Crosscheck: factor driven approach
FTE = Full-Time Equivalent

## Slide 9: SEPM as a Fixed Cost
Why not use a parametric technique to estimate Non-DCTI?
  I.e.: why not use Excel’s “Analysis ToolPak” or ACEIT Costat to develop a correlation between Non-DCTI Hours (or cost) and an objective measure (ESLOC, DSLOC, weight, volume, etc.)?
SEPM is a predominately fixed and recurring cost:
  SEPM does not scale directly with the project’s objective measures
  E.g.: for every additional ESLOC of a project, there is not a proportional increase in the number of SEPM FTEs
  Often varies significantly depending on the project/contractor/vendor
However, SEPM does scale with the total number of concurrent baselines under development:
  E.g.: if the system under development will be integrated onto 2 different host aircraft types; then, the total SEPM costs will be greater than if the system was integrated onto 1 host aircraft type
  I.e.: costs for integrating a system onto 2 platforms > 1 platform
Because SEPM is a predominately fixed & recurring cost, estimating it best served by a bottom up methodology

## Slide 10: Collecting SEPM Actuals by Labor Category
When collecting SEPM FTE actuals from contractors/vendors:
  Identify FTEs by constituent labor categories
  E.g. a small software development effort could be:

## Slide 11: Software Development Cost Rosetta Stone
Variable, Non Recurring Costs
Fixed, Recurring Costs
Design, Code, Test, & Integration (DCTI)
Non-DCTI
(a.k.a. software SEPM)
Analog in MIL-STD 881C:
Prime Mission Product (PMP)
Software Development Cost Element
Structure:
Inc. in Systems Engineering
Program Management (SEPM)
Analog in IEEE/EIA 12207:
System-level Activities: System Requirements Analysis, System Architecture Analysis, System Integration, System Qualification Testing, Software Installation, & Software Acceptance Support
Element-level Activities: Software Requirements Analysis, Software Architecture Analysis, Detailed Design, Code & Unit Test, Software Integration, Software Qualification Testing, Part of System Integration, & Process Implementation
= (ESLOC * Growth) / Productivity * Labor Rate
= FTEs/year * Years of development * Labor Rate
Analog in CSDRs:
Scope Captured in SRDR (2630 forms)
Scope Captured in CCDR
(1921 & 1921-1 forms)
Analog in Production Estimating:
Touch Labor
Support-to-Touch
SEPM
Software Development Cost = Variable Costs + Fixed Costs
Slide POC: james.robert.black@gmail.com

## Slide 12: Recommendations
Get as much visibility as possible when collecting SEPM FTE actuals from contractors/vendors:
  Separately identify recurring and non-recurring FTEs
  Separately identify FTEs performing software, hardware, and integration related activities
  Identify FTEs by constituent labor categories (i.e. how many project managers, systems architects, business analysts, domain specialists or subject matter experts, etc.)
  If there are multiple concurrent spirals/increments or baselines, identify how the total SEPM is split between them
Partition a software cost estimate into two components:
  Variable, non-recurring costs - DCTI, i.e. costs dependent on software size
  Fixed, recurring costs – Software SEPM or Non-DCTI , i.e. costs independent of software size
Visibility & Partitioning are useful when comparing cost estimates and briefing results to senior leaders

## Slide 13: Summary
The WBS is the foundation and a common WBS speeds the uptake of information for the cost estimate’s audience
When estimating software costs: be diligent in identifying how effort is allocated to DCTI, Non-DCTI and/or SEPM
IEEE 12207 is useful when differentiating between SEPM & DCTI
Because SEPM is a predominately fixed & recurring cost, estimating it best served by a bottom up methodology
Factor driven estimating methodologies are useful in the absence of time/data and can be useful crosschecks

## Slide 14
Backup

## Slide 15: SEPM Scaling with # of Platforms
SEPM does scale with the total number of concurrent baselines under development:
  E.g.: if the system under development will be integrated onto 2 different host platform types; then, the total SEPM costs will be greater than if the system was integrated onto 1 host platform type
  I.e.: costs for integrating a system onto 2 platforms > 1 platform
SEPM is a predominately fixed cost, but does scale with the # of platform types
Example where a second host platform
is added in Year 4 of development:

## Slide 16: IEEE Standard 12207
DCTI
Element-level software development
DCTI
Element-level software development
SEPM
System-level activities related to software, hardware, and integration
SEPM
System-level activities related to software, hardware, and integration